## Sheet1
Name of State | Status update on Disincentves |  |  |  | Status update on Incentives
| Rational deployment of HR with the highest priority accorded to high focus districts and delivery points/priority facilities | Facility wise performance audit and corrective action based thereon. | Gaps in implementation of JSSK | Continued support under NRHM for 2nd ANM would be contingent on improvement on ANC coverage and immunization as reflected in MCTS. | Responsiveness, transparency and accountability | Quality assurance | Inter-sectoral convergence | Recording of vital events including strengthening of civil registration of births and deaths | Creation of a public health cadre | Policy and systems to provide free generic medicines to all in public health facilities
Manipur | Out of 05 hill districts four Districts are under High Focus and remaining District i.e. Senapati though its on National Highway but due to difficult terrain & topography it may also be considered under HFDs. | Performance Based Honorarium to the contractual staffs being strictly monitored . Complusory report to assess performnce of each contractual is called quarterly from concerned DCs & CMOs. | Districts started implementing. No referral transport service available in State Govt.Order placed for the 40 ambulaces approved in current year, expected by end of Jan'13. | MCTS begins in 06 districts. Total ANC coverage could not be taken up from MCTS as it is not implemented in 03 hill districts where the internet connectivity is major isssue. | Regularly updated in State NRHM website for any activities carried out under NRHM. Proper procurement procedure as per guidelines is followed. DLVMC constituted in all districts, convened meeting regularly. | Formed in alll Districts & State Regular monitoring visits is planned in 2013-14. | ARSH Program tie up with Social welfare and eductaion dept… | Continous meetings headed by Additional Director (PH) under Directorate of Health is held. | Yet to be taken up | Procurement process for supplying free drugs & medicines through NRHM is under process. Approval of Governing Body awaited.
| Decentralized/ districtwise recruitment done. Staffs are non transferable except in excepttional cases. Difficult area allowances provided to NRHM staffs.All recruited are done through open advertisement. | Deputy Director identified especially for conducting performance audit of health facilities. In 2012-13 another DH has been upgraded to FRU level. | EDL List is prepared. Alreay tie up with Rajasthan Medical Sciences coorporation (RMSC), awaited for the approval of GB. | To begin with District Head Qtr. Area in 2013-14 for the remaining districts. |  |  | Solar power plant/ solar lamp supplied by MANIREDA through sharing of fund. | Regularly reports are compiled and submitted to concerned division at GOI
| NRHM has hardly 10 Doctors, maximum are underHealth Directorate. DHS are updated on the rationalzation of the doctors, base on the districts requirement rationalization of doctors is initiated. | From 18 PHCs functioning 24x7, at present 25 PHCs are doing round the clock conducting delivery services. | Full implementation of JSSK will take another 2-3 months. Will also start in the identified delivery point only.