Background Information Required for Approval of State PIPs for 2013-14

FMR Code: B 15.1: Community Monitoring

| Number of Visioning workshops for community monitoring held so far in the state (UPTO 2012-13) | 7 |
| --- | --- |
| Number of Visioning workshops for community monitoring planned for 2013-14 if any at State/ Distrit/ Block level and other | 1 at District & 3 in 3 Blocks |
| Officer responsible for community monitoring at each level (Designation). Also mention if the officer has any other charges. |  |
| Whether a nodal agency at State has been identified already. If yes, then please give details. |  |
| Whether a State chapter of the Advisory Group of Community Action |  |
| Whether Community Monitoring is being undertaken in the state for health (both under NRHM and under State budget - please specify) |  |
| Number of blocks where Community Based Monitoring was being implemented in the State - activities undertaken |  |
| Number of districts where Community Based Monitring was being implemented - activities undertaken |  |
| Whether social audit / Jan Sunwai is being undertaken anywhere in the state for health |  |

Measures to increase Accountability to community:

| Whether citizen's charter is prepared and displayed on public domain. If yes, provide link: | At DH, CHCs & PHCs |
| --- | --- |
| Whether a grievance redressal mechanism is set-up. If yes, pleas eprovide details. | No |
| Whether an ombudsman is appointed for grievance redressal. If any please provide further details. | No |
| Whether a portal is prepared for mandatory disclosure of information needed as per instructions of CIC | No |

FMR Code: B-15.3- Monitoring & Evaluation

| Major Head | Minor Head |  | Budget in Rs | Details (including cost per unit) | Remarks | Amount approved in 2012-13 | Actual expenditure in 2012-13 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1.Strengthening of M&E/HMIS/ MCH Tracking | Salaries of M&E, MIS & Data Entry Consultants – PHC data asst. formerly Block HMIS asst. (Salaries of DDM/ DNM&EO and BDM/ BNM&EO are reflected at FMR Code-A.10 – Programme Management) | 1.1 | 15.288 | Rs. 18200/ month for 7 PHC Data Asst. | The HMIS/ MCTS activities need to be implemented from the PHC levels for timely submission M&E reports and live data capturing of MCTS. Therefore, the 3 Block HMIS Asst. will be relocated at the PHCs and for the remaining 4 PHC are being proposed | 5.04 @ Rs.14000/ month for 3 HMIS Asst. | 1.067 (State has given @Rs.8000/ month only) |
|  | Mobility for M & E Officers | 1.2 | 7.2 L | DC=360000, DNM&EO=180000, 3 BNM&EO=180000 | Monitoring visits by DC/ Chairman, DHS, District M&E Officer and Block M&E Officers are necessary for timely supervision of recording and reporting system and also for functionality of the facilities. | 1.35 | 0.0 (Fund not released by state) |
|  | Workshops/Training on M & E | 1.3 | 1.2 L | DIST=30000 3 BLOCK=90000 | Training of Official/ staff are necessary for timely updation of M&E report format and to check the accuracy and validity of the M&E reports | 1.6 | 0.8 (50% released by state) |
|  | M&E Studies | 1.4 |  |  |  |  |  |
|  | Monthly meeting at District and Block | 1.5 | 1.68L | DIST=60000, 3 BLOCK=168000 | 5000/M at Dist 3000/M at 3 Blocks | 1.68 | 4 months released |
| 2. Procurement of HW/SW and other equipments | Hardware/Software Procurement | 2.1 | 3.15 L | Laptop @ Rs. 45000 for 7 PHC Data Asst. | The power supply is not regular and need power backups for HMIS/ MCTS activities |  |  |
|  | Internet connectivity | 2.2 | 4.5L | V-Set @Rs. 150000 (1 at DHQ and 2 at Bishnupur and Moirang Blocks) | At present all the HMIS and MCTS activities are working with Internet data cards (without broad band), making the implementations very difficult and slow. IDSP not functional, CSC not functioning & SWAN installed only at SDO/BDO & other administrative offices not at the Health Facilities. |  |  |
|  | Annual Maintenance | 2.3 | 2.892 L | Rental of V-Set @Rs.5000/month for 3 V-Sets & 7 data cards @Rs.1300/month |  | 0.624 rental for data cards | 0.314 (only 4 month rental received) |
|  | Operational Costs (consumables etc) | 2.4 | 1.3L | DIST = 40000, 3 BLOCK = 90000 | For replacing/ refilling of Printer Cartridge and other P/S activities for HMIS/MCTS | 0.84 | 0.09 (only Rs.0.24 received) |
|  | Quarterly meeting of DPeMT and District HMIS Task Force | 2.5 | 0.4 L | Rs. 10000 per meeting | For review of HMIS and MCTS performance and necessary actions |  |  |
|  | Visioning workshop for Community Monitoring | 2.6 | 1.2 L | Rs. 30000/ Dist. & 3 Blocks |  |  |  |
| 3.Operationalising HMIS at Sub District level | Review of existing registers – to make them compatible with National HMIS | 3.1 | 0.86 L | 43 copies X 10 regs. X Rs. 200 | The district is facing problems in maintaining the records/ registers as no registers are supplied since 2011-12 |  |  |
|  | Printing of new registers/Forms | 3.2 |  |  |  |  |  |
|  | Training of staff | 3.3 |  |  | Ref. 1.3 |  |  |
| 4.Operationalising MCH tracking | Printing and reproducing Registers/ Forms | 4.1 |  |  | Ref. 2.4 |  |  |
|  | Capacity building of teams | 4.2 |  |  |  |  |  |
|  | Ongoing review of MCH tracking activities | 4.3 |  |  |  |  |  |
|  | Monitoring data collection and data quality | 4.4 |  |  |  |  |  |
|  | Incentives for ASHAs for mobilization of PW & Children for timely registration at MCTS | 4.5 | 13.236 | Rs. 50 for timely mobilization and registration of PW & Child and Rs. 100 for full Service of PW & Child (PW target =4644 and Infant target = 4180) | The ASHA incentives were given @Rs. 100 per case of PW & Child but since 2012-13 no incentives were provided (as not approved) due to which timely registration of PW and Child reduces. Moreover, ASHAs are the voluntary worker getting no monthly fixed salary. |  |  |
|  | Total |  | 54.814 |  |  |  |  |