Background Information Required for Approval of State PIPs for 2013-14

F.M.R. Code: A.3- Family Planning

FP: Annexure -1

| SN. | Indicator | Target / ELA 2012-13 | Achievements (as on Oct 12) | Remarks |
| --- | --- | --- | --- | --- |
| 1 | Goal (target): |  |  |  |
| 1.1 | Reduction in TFR – 2013 |  |  |  |
| 2 | Service delivery (ELA): |  |  |  |
| 2.1 | IUCD: |  |  |  |
| 2.1.1 | Post-partum IUCD | 45 | 0 |  |
| 2.1.2 | Interval IUCD | 500 | 380 |  |
| 2.2 | Sterilisation: |  |  |  |
| 2.2.1 | Tubectomy | 128 | 0 |  |
| 2.2.2 | Post-partum sterilisation (subset of tubectomy) | 54 | 0 |  |
| 2.2.3 | Vasectomy | 27 | 25 |  |
| 3 | Training of personnel (target): |  |  |  |
| 3.1 | Post-partum IUCD |  |  |  |
| 3.1.1 | MO | 6 | 3 |  |
| 3.1.2 | SN/ ANM | 48 | 24 |  |
| 3.2 | Interval IUCD |  |  |  |
| 3.2.1 | MO | 12 | 0 |  |
| 3.2.2 | SN | 60 | 0 |  |
| 3.2.3 | ANM/ LHV |  |  |  |
| 3.3 | Minilap |  |  |  |
| 3.4 | NSV |  |  |  |
| 3.5 | Laparoscopic |  |  |  |
| 4 | Others (target): |  |  |  |
| 4.1 | Appointment of FP Counsellors | 11 | 6 |  |
| 4.3 | Regular reporting of the scheme of “home delivery of contraceptives by ASHAs” |  |  |  |
| 4.4 | Fixed Day Services for IUCD | 6 | 0 |  |
| 4.5 | Fixed Day Services for Sterilisation | 1 | 0 |  |

FP: Annexure -II

FORMAT FOR FAMILY PLANNING FOR ACTIVITIES FOR 2013-14 PIP

| SN. | STRATEGY / ACTIVITY | Cumulative achievement (as on 31st March 2012) | PLANNED | ACHIEVED | WORK PLAN | SCHEDULED/ Trg. LOAD | BUDGET (In lakhs) | REMARKS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2012-13 | 2013-14 |
| 1 | FAMILY PLANNING MANAGEMENT |
| 1.1 | Review meetings on Family Planning performance and initiatives at the state and district level (periodic; including QAC meetings)) | NR | 1 | 1 | Twice a year | July 2013 and Jan 2014 with 40 participants | 0.4 |  |
| 1.2 | Monitoring and supervisory visits to districts/ facilities | NR | 0 | 0 | 4 times a year | Quarterly | 0.40 |  |
| 1.3 | Orientation workshops on technical manuals of FP viz. standards, QA, FDS approach, SOP for camps, Insurance etc. | NR | 1 | 0 | 1 X 3Block |  | 1.20 |  |
| 2 | SPACING METHOD (Providing of IUCD services by districts) |
| 2.1 | Plan for providing FDS (Fixed Day Static) IUCD services at health facilities in districts (at least 2 days in a week at SHC and PHC level) – number of facilities to be provided |  | 8 | 0 | 8 facilities | Every Monday | 0.30 | ASHA/ Motivator fee @Rs. 50 for 600 beneficiaries |
| 2.2 | No. of IUCD camps in districts | NR | 0 | 0 | 7 |  | 0.70 | 1 camp @Rs. 10,000 |
| 2.3 | Compensation for IUCD | NR |  |  |  |  |  |  |
| 2.4 | Plan for strengthening PPIUCD services | NR |  |  |  |  |  |  |
| 3 | TERMINAL/LIMITING METHODS ( Providing sterilisation services in districts) |
| 3.1 | Plan for facilities providing FEMALE sterilisation services on fixed days at health facilities in districts (number of facilities) |  |  |  | 1 (DH) |  |  |  |
| 3.2 | Plan for facilities providing NSV services on fixed days at health facilities in districts (number of facilities) |  |  |  | 1 DH + 2 CHCs |  |  |  |
| 3.3 | Number of FEMALE Sterilisation camps in districts. | NR | 1 | 0 | 2 | Half yearly | 0.26 |  |
| 3.4 | Number of NSV camps in districts. | NR | 1 | 3 | 2 | Half yearly | 0.26 |  |
| 3.5 | Compensation for sterilisation (female) | NR | 128 | 0 |  | 50 | 0.55 | @Rs. 1100/case |
| 3.6 | Compensation for sterilisation NSV (male) | NR | 27 | 25 |  | 200 | 3.00 | @Rs. 1500/case |
| 3.7 | Additional mobility support to surgeon’s team (if required) | NR |  |  |  |  |  |  |
| 3.8 | Accreditation of private centres/ NGOs for sterilization services (number accredited) | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| 3.9 | Plan for post partum sterilisation | NR | 54 | 0 |  | 80 |  |  |
| 4 | Placement of counsellors at high case load facilities |  |  |  |  |  |  |  |
| 5 | Social marketing of contraceptives | NR |  |  |  |  |  |  |
| 6 | FAMILY PLANNING TRAINING |
| 6.1 | IUCD 380 A Insertion training |
| 6.1.1 | TOT for IUCD 380 A insertion |  | 3 | 2 |  | 0 |  | State |
| 6.1.2 | Training of Medical officers in IUCD 380 A insertion |  | 6 | 0 | 2 | 12 in 2 batch |  | State |
| 6.1.3 | Training of staff nurses in IUCD 380 A insertion |  | 60 | 0 | 2 | 12 in 2 batch |  | State |
| 6.1.4 | Training of ANMs / LHVs in IUCD 380 A insertion |  | 33 | 0 | 4 | 24 in 4 batch |  | State |
| 6.1.5 | Refresher training in IUCD 380 A |  |  |  |  | 48 in 8 batch |  | State |
| 6.2 | PPIUCD training |
| 6.2.1 | TOT for PPIUCD insertion |  |  |  |  |  |  |  |
| 6.2.2 | Training of Medical officers in PPIUCD insertion |  |  |  | 1 | 3 MO |  | State |
| 6.2.3 | Training of staff nurses in PPIUCD insertion |  | 0 | 0 |  | 6 SN |  |  |
| 6.3 | Cu IUCD 375 Insertion training |
| 6.3.1 | TOT for Cu IUCD 375 insertion |  | 0 | 0 |  | 3 SMO |  |  |
| 6.3.2 | Training of Medical officers in Cu IUCD 375 insertion |  | 0 | 0 |  | 10 MO |  |  |
| 6.3.3 | Training of staff nurses in Cu IUCD 375 insertion |  | 0 | 0 |  | 20 SN |  |  |
| 6.3.4 | Training of ANMs / LHVs in Cu IUCD 375 insertion |  | 0 | 0 |  |  |  |  |
| 6.4 | Laparoscopic Sterilisation Training |
| 6.4.1 | TOT on laparoscopic sterilisation |  | 3 | 1 |  | 1 |  |  |
| 6.4.2 | Laparoscopic sterilisation training for service providers (gynaecologists /surgeons) |  | 0 | 0 | 0 | 0 | 0 | 0 |
| 6.4.3 | Refresher training (if required) |  | 0 | 0 | 0 | 0 | 0 | 0 |
| 6.5 | Minilap Training for MOs/ MBBS |
| 6.5.1 | TOT on Minilap |  | 0 | 0 |  | 2 |  |  |
| 6.5.2 | Minilap training for service providers (medical officers) |  | 0 | 0 |  |  |  |  |
| 6.5.3 | Refresher training (if required) |  |  |  |  |  |  |  |
| 6.6 | Non-Scalpel Vasectomy (NSV) Training |
| 6.6.1 | TOT on NSV |  | 4 | 4 |  | 0 |  |  |
| 6.6.2 | NSV training for medical officers |  | 12 | 6 |  | 12 |  |  |
| 6.6.3 | Refresher training (if required) |  | 0 | 0 | 0 | 0 | 00 | 0 |
| 6.7 | No. of Contraceptive Update trainings for health providers in the districts |  |  |  |  |  |  |  |
| 6.8 | Other family planning trainings (please specify) |  |  |  |  |  |  |  |
| 7 | ‘World Population Day’ celebration (such as mobility, IEC activities etc.): funds earmarked for district and block level activities. | NR | 1 | 1 | 1 | September 2013 | 0.9 |  |
| 8 | BCC/ IEC activities – Campaigns/ melas / print/ audio/ video materials for family planning | NR | 0 | 0 | 0 | 0 | 0 | 0 |
| 9 | PROCUREMENT of DRUGS/MATERIALS |
| 9.1 | NSV Kits |  | 24 | 0 | 24 |  |  | State |
| 9.2 | IUCD insertion Kits |  |  |  | 43 |  |  | State |
| 9.3 | PPIUCD (Kelly’s) forceps |  |  |  | 6 |  |  | state |
| 9.4 | Minilap Set |  |  |  |  |  |  |  |
| 9.5 | Procurement/ repair of laparoscopes |  |  |  |  |  |  |  |
| 10 | Strengthening of programme management structures | NR |  |  |  |  |  |  |
| 11 | Performance based rewards to institutions and providers for FP performance at state and district level | NR | 0 | 0 |  |  |  |  |
| 12 | PROMOTIONAL SCHEMES |
| 12.1 | Delivery of contraceptives by ASHA at door step | NR |  |  |  |  |  |  |
| 12.2 | Scheme of “utilising services of ASHAs for delaying first child birth after marriage and have 3 year’s spacing between 1st and 2nd child” | NR |  |  |  |  |  |  |
| 13 | Other activities | NR |  |  |  |  |  |  |